## Slide 1
JHBI DaaS
Data as a Service Platform
Quarterly Roadmap · Q4 FY26 – Q3 FY28
8
workstreams
8
quarters
2-stage
GCP architecture
1,660
addressable FIs
Data Science & Analytics Team · Confidential

## Slide 2
JHBI DaaS — Two-Stage GCP Architecture
STAGE 1 — JH Internal Data Lake
Shared GCP Project · JH-internal use
BigQuery Data Lake
Medallion architecture: Bronze/Silver/Gold layers
Alation Data Catalog
Governed, discoverable, audit-ready data assets
Test Data Management
Synthetic + anonymized data for dev/QA environments
Pub/Sub Streaming
Real-time ingestion from all JH payment + core systems
Data Quality & Lineage
Great Expectations + Alation lineage tracking
Internal DS Tooling
Vertex AI · MLflow · Feature Store · Experiment tracking
→
data
flow
STAGE 2 — Single-Tenant FI Projects
Per-FI GCP Project · Complete data isolation
FI Data Lake (BigQuery)
FI-scoped Bronze/Silver/Gold · core + payments + Banno
Self-Service Portal
FI banker UI: score explorer, thresholds, NL2SQL, export
Alation Catalog (per-FI)
FI-branded data dictionary · lineage · governance
Entity Resolution
Customer dedup + household linking across FI data
NL2SQL + NL2Insight
Natural language → queries → narrative insights (Gemini)
DS App Suite
Churn Sentinel · Zelle Memo · CommercialSignal + 4 more
2

## Slide 3
JHBI DaaS · Master Roadmap — Q4 FY26 through Q3 FY28
FOUNDATION
STAGE 1+2 BUILD
SCALE & AI
FULL PLATFORM
Q4 FY26
Apr–Jun 26
Q1 FY27
Jul–Sep 26
Q2 FY27
Oct–Dec 26
Q3 FY27
Jan–Mar 27
Q4 FY27
Apr–Jun 27
Q1 FY28
Jul–Sep 27
Q2 FY28
Oct–Dec 27
Q3 FY28
Jan–Mar 28
INFRA
Infrastructure
LEGAL
Legal & Compliance
STAFF
Contractors & Staffing
INGEST
Data Ingestion
SECURE
Sensitive Data Handling
REPORT
Reporting & Dashboards
AI/NLP
AI Integration
DS APPS
Data Science Apps
3

## Slide 4
Q4 FY26 · Stage 1+2 Launch
April – June 2026
STAGE 1 & 2 PARALLEL LAUNCH · GCP setup · Legal framework · Team hiring begins · App architecture
Infrastructure
GCP shared project · VPC/networking · BigQuery lake schema · Stage 2 single-tenant project template
Sensitive Data Handling
PII inventory completed · DLP policy design · tokenization architecture · data residency requirements
Legal & Compliance
DPA templates drafted · FI data rights framework · NCUA/FFIEC compliance review initiated
Reporting & Dashboards
Alation license procured · shared project catalog setup · BI tool selection (Looker/Tableau)
Contractors & Staffing
13 FTE hiring plan finalized · JDs posted · recruiting vendors engaged
AI Integration
Entity resolution architecture · NL2SQL design (Vertex AI/Gemini) · LLM evaluation
Data Ingestion
ACH/payment rail connector specs · Pub/Sub streaming design · ingestion architecture for Stage 1+2
Data Science Apps
AutoGluon + CatBoost + XGBoost framework · SHAP explainability layer · Stage 2 ML pipeline design
4

## Slide 5
Q1 FY27 · First Data Flowing
July – September 2026
STAGE 1: First ingestion live · STAGE 2: Pilot FI projects provisioned · Team onboarding
Infrastructure
CI/CD pipelines · Pub/Sub streaming live · Vertex AI platform · Stage 2: 3 pilot FI projects provisioned
Sensitive Data Handling
Tokenization live for payment data · PII masking in BigQuery · SOC 2 Type II prep begins
Legal & Compliance
Pilot FI MSAs signed (3–5 FIs) · data sharing agreements · SR 11-7 model risk documentation started
Reporting & Dashboards
Alation cataloging all ingested data assets · first exec KPI dashboards deployed
Contractors & Staffing
First 5 hires onboarded: DS Lead · 2× Data Eng · 2× ML Eng
AI Integration
Entity resolution MVP — customer dedup across payment data · internal testing begins
Data Ingestion
ACH + Zelle pipelines live in Stage 1 (BigQuery) · same feeds mirrored to Stage 2 FI projects
Data Science Apps
Churn Sentinel ACH Phase 1 deployed to pilot FI Stage 2 projects · SHAP scores live
5

## Slide 6
Q2 FY27 · Core Banking + Portal Alpha
October – December 2026
STAGE 1: All payment rails + core banking · STAGE 2: 5–10 FIs · Self-service portal alpha
Infrastructure
Monitoring/observability (Datadog/GCP ops) · autoscaling · Stage 2 expanded to 10 FI projects
Sensitive Data Handling
Core banking PII handling · column-level encryption · audit logging · FI-level data isolation verified
Legal & Compliance
Data sharing agreements executed for 10 FIs · FFIEC attestation in progress · model cards drafted
Reporting & Dashboards
FI self-service portal alpha · banker score explorer MVP · drift monitoring dashboards
Contractors & Staffing
Full 13 FTE team onboarded · onboarding ramp complete
AI Integration
NL2SQL MVP — natural language → BigQuery · internal analyst testing · entity resolution to production
Data Ingestion
All payment rails live (Wires, iPay, SmartPay, Payrailz) · Core Banking (jhaEnterprise/Symitar) pipeline begins
Data Science Apps
Zelle Memo Intelligence + CommercialSignal deployed to Stage 2 · CatBoost models in production
6

## Slide 7
Q3 FY27 · Core Banking Live + AI MVP
January – March 2027
STAGE 1: Core banking fully operational · STAGE 2: 20+ FIs · NL2SQL + NL2Insight to FI portal
Infrastructure
MLOps platform (Vertex Pipelines + model registry) · drift monitoring · Stage 2: 25 FI projects
Sensitive Data Handling
SOC 2 Type II audit window · data retention policies live · FI-level isolation pen-tested
Legal & Compliance
SOC 2 Type II audit begins · NCUA examination readiness · SR 11-7 documentation complete
Reporting & Dashboards
FI portal beta · Alation fully cataloged · NL-powered report generation MVP · benchmarking views
Contractors & Staffing
Year 1 steady state · backfill planning for Year 2 growth roles
AI Integration
NL2Insight MVP — narrative summaries from data · FI portal AI assistant beta · entity resolution GA
Data Ingestion
Core Banking (jhaEnterprise / Symitar) live in Stage 1 · Banno digital pipeline design begins
Data Science Apps
Churn Sentinel+ (Core + digital signals) · Gen. Wealth Deflection deployed · XGBoost ensemble
7

## Slide 8
Q4 FY27 · Banno Live + AI GA
April – June 2027
STAGE 1: All data sources live · STAGE 2: 50 FIs · NL2SQL + NL2Insight GA · AI copilot in portal
Infrastructure
Multi-region GCP config · HA/DR runbooks · Stage 2: 50 FI projects · infrastructure cost baseline set
Sensitive Data Handling
SOC 2 Type II report issued · continuous compliance monitoring dashboard live · NCUA exam ready
Legal & Compliance
SOC 2 Type II complete · full legal stack for commercial launch · bundle pricing agreements
Reporting & Dashboards
FI portal GA · NL2SQL + NL2Insight live in portal · full self-service analytics for FIs
Contractors & Staffing
Year 2 hiring plan (scale roles: ADS x2, API Dev x1) · contractor pipeline refreshed
AI Integration
NL2SQL + NL2Insight GA · AI copilot embedded in FI dashboards · proactive anomaly narration
Data Ingestion
Banno Digital + Lending data live in Stage 1 + Stage 2 · all 5 JH data layers operational
Data Science Apps
Anomaly Detection + FI Decision Studio GA · AutoGluon unsupervised → supervised pipeline live
8

## Slide 9
Q1 FY28 · $1.25M ARR Milestone
July – September 2027
STAGE 2: 100 FIs · Full app suite live · $1.25M ARR · AI-powered recommendations in production
Infrastructure
Full scale HA/DR · Stage 2: 100+ FI projects · GCP cost optimization · shared infrastructure efficiencies
Sensitive Data Handling
External compliance audit · FI penetration testing · data residency audit across 100 Stage 2 projects
Legal & Compliance
Ongoing compliance audits · FI-level data rights renewals · open data legal framework (NCUA 5300)
Reporting & Dashboards
Full analytics suite · FI benchmarking live · embedded analytics in JH platform surface
Contractors & Staffing
Additional contractors for scale (Data Eng x2, ML Eng x1) · specialist roles for Horizon apps
AI Integration
Advanced AI: proactive insights, Next Best Action recommendations · AI copilot fully embedded
Data Ingestion
Cross-FI aggregated intelligence layer · anonymized benchmarking feeds · NCUA 5300 open data begins
Data Science Apps
★ Full suite 5 apps live · $1.25M ARR · 102 FI subscriptions · 6.1% penetration of 1,660 FI base
9

## Slide 10
Q2 FY28 · Horizon Apps + Scale
October – December 2027
STAGE 2: 200 FIs · Horizon pipeline apps launching · Bundle pricing · $1.64M ARR
Infrastructure
Stage 2: 200 FI projects · platform optimization · per-FI cost targets met · shared service efficiencies
Sensitive Data Handling
NCUA examination cycle · FI-by-FI compliance dashboard · ongoing pen testing cadence
Legal & Compliance
Bundle/Intelligence+ pricing agreements · data marketplace legal framework · FI co-selling agreements
Reporting & Dashboards
Custom FI dashboards · white-label portal for larger FIs · embedded benchmarking in JH platform
Contractors & Staffing
Team at full Year 2 scale · Horizon app specialists onboarded
AI Integration
AI recommendations at scale · NL2Insight cross-FI narratives · copilot usage analytics
Data Ingestion
Data quality SLAs enforced (99.9% pipeline uptime) · automated lineage tracking via Alation
Data Science Apps
Horizon apps: Cross-Sell Propensity · Fraud Ring Detection · Deposit Runoff · $1.64M ARR
10

## Slide 11
Q3 FY28 · Full Platform Scale
January – March 2028
STAGE 2: 300+ FIs · Open data expansion · Year 2 bundle pricing live · Horizon pipeline in GA
Infrastructure
Next-gen infra (GCP AI Hypercomputer for model training at scale) · open data infrastructure
Sensitive Data Handling
Full compliance framework operational · continuous FedRAMP alignment · multi-cloud data residency
Legal & Compliance
Open data legal frameworks (NCUA 5300, FFIEC public data) · Horizon app MSAs · Year 3 planning
Reporting & Dashboards
Advanced reporting: predictive benchmarks · FI peer analysis · board-ready AI narrative reports
Contractors & Staffing
Year 3 hiring plan · specialist AI/ML roles · FI success manager team buildout
AI Integration
Full AI copilot in FI portal · LLM fine-tuning on JH FI domain · multi-modal insights
Data Ingestion
NCUA 5300 open data pipeline · external FI data partnerships · data marketplace connectors
Data Science Apps
Horizon apps GA: Cross-Sell · Fraud Ring · Deposit Runoff · Overdraft · Sentiment · Year 3 roadmap
11