## Slide 1
JHBI
Data Science Platform
Quarterly Roadmap · Q3 FY26 – Q2 FY28
8
quarters
1,660
addressable FIs
7 apps
delivering by FY28
$1.25M
ARR target Q1 FY28
Data Science & Analytics Team · Confidential

## Slide 2
JHBI · Master Delivery Roadmap — Q3 FY26 through Q2 FY28
PHASE 1 — Foundation
PHASE 2 — Core Applications
PHASE 3 — Scale & Expand
Q3 FY26
Jan–Mar 26
Q4 FY26
Apr–Jun 26
Q1 FY27
Jul–Sep 26
Q2 FY27
Oct–Dec 26
Q3 FY27
Jan–Mar 27
Q4 FY27
Apr–Jun 27
Q1 FY28
Jul–Sep 27
Q2 FY28
Oct–Dec 27
DATA
INGESTION
ACH / EPS
Zelle / JHA PayCenter
JH Wires + iPay + SmartPay + Payrailz
Core Banking (jhaEnterprise / Symitar)
Banno Digital + Lending
APP
DELIVERY
Churn Sentinel (ACH Phase 1)
Zelle Memo Intelligence
Churn Sentinel+ (Core & Digital)
CommercialSignal
Generational Wealth Deflection
Anomaly Detection
FI Decision Studio (AutoML GA)
2

## Slide 3
Q3 FY26 · Phase 1: Foundation
January – March 2026
PHASE 1 — Foundation · Hire team · stand up cloud platform · activate first payment rails
DATA INGESTION
ACH / EPS
✓ Activated — direct deposit cadence monitoring live
Zelle / JHA PayCenter
✓ P2P, Zelle, RTP, FedNow feeds connected
JH Wires + iPay + SmartPay
Coming Q4 FY26
Core Banking (jhaEnterprise / Symitar)
Pipeline prep — launches Q1 FY27
Banno Digital + Lending
Planned Q3 FY27
APP DELIVERY
Churn Sentinel — ACH Phase 1
Building: ACH cadence + originator change detection
Zelle Memo Intelligence
Building: NLP compliance pipeline (DistilBERT/RoBERTa)
CommercialSignal
Planned Q1 FY27
Generational Wealth Deflection
Planned Q2 FY27
Anomaly Detection / FI Decision Studio
Planned Q3 FY27
3

## Slide 4
Q4 FY26 · Phase 1: Foundation Complete
April – June 2026
PHASE 1 — Foundation · All payment rails operational · builds completing for Q1 FY27 launch
DATA INGESTION
ACH / EPS
✓ Operational
Zelle / JHA PayCenter
✓ Operational
JH Wires + iPay + SmartPay + Payrailz
✓ All payment rails activated — anomaly detection enabled
Core Banking (jhaEnterprise / Symitar)
Pipeline preparation — Q1 FY27 launch ready
Banno Digital + Lending
Planned Q3 FY27
APP DELIVERY
Churn Sentinel — ACH Phase 1
✓ Build complete — validation & staging in progress
Zelle Memo Intelligence
✓ Build complete — preparing for Q1 FY27 launch
CommercialSignal
Planned Q1 FY27
Generational Wealth Deflection
Planned Q2 FY27
Anomaly Detection / FI Decision Studio
Planned Q3 FY27
4

## Slide 5
Q1 FY27 · Phase 2: Core Applications
July – September 2026
PHASE 2 — Core Applications · Core banking online · Zelle Memo Intelligence launches · ARR begins
DATA INGESTION
All Payment Rails
✓ Fully operational
Core Banking (jhaEnterprise / Symitar)
★ LAUNCHING — Core txns, deposits, loans fully connected
Banno Digital + Lending
Planned Q3 FY27
APP DELIVERY
Zelle Memo Intelligence
★ LAUNCHING — Live for 260 Zelle-enabled FIs · $48.5K ARR
Churn Sentinel — ACH Phase 1
✓ Operational across all 1,660 FIs
Churn Sentinel+ (Phase 2)
Building: Core & Banno signal enrichment
CommercialSignal
Starting build — SMB conversion model
Anomaly Detection / FI Decision Studio
Planned Q3 FY27
5

## Slide 6
Q2 FY27 · Phase 2: Core Applications
October – December 2026
PHASE 2 — Core Applications · Churn Sentinel & CommercialSignal launch · ARR $293K
DATA INGESTION
All Payment Rails
✓ Fully operational
Core Banking (jhaEnterprise / Symitar)
✓ Operational — enriching Churn Sentinel & CommercialSignal
Banno Digital + Lending
Planned Q3 FY27
APP DELIVERY
Zelle Memo Intelligence
✓ Operational — ARR $87.3K and growing
Churn Sentinel+
★ LAUNCHING — Core + digital signals · $205.5K ARR
CommercialSignal
★ LAUNCHING — Personal-to-business conversion model live
Generational Wealth Deflection
Building — household linkage + wealth concentration model
Anomaly Detection / FI Decision Studio
Planned Q3 FY27
6

## Slide 7
Q3–Q4 FY27 · Phase 3: Scale & Expand
January – June 2027
PHASE 3 — Scale & Expand · Banno Digital live · Final 3 apps launching · ARR $900K+
DATA INGESTION
All Payment Rails
✓ Fully operational
Core Banking
✓ Fully operational
Banno Digital + Lending
★ LAUNCHING — Session behavior, loan data, Banno signals live
Cross-FI Benchmarking
✓ Network intelligence across all 1,660 FIs
APP DELIVERY
Zelle Memo · Churn Sentinel+ · CommercialSignal
✓ Operational & scaling — combined ARR $620K+
Generational Wealth Deflection
★ LAUNCHING Q3 FY27 — Household coverage model live
Anomaly Detection
★ LAUNCHING Q3 FY27 — Real-time streaming fraud engine
FI Decision Studio
★ GA RELEASE Q3 FY27 — AutoML, SHAP, rule authoring, API deploy
Horizon Pilots
Cross-Sell Propensity, Overdraft Prediction, Sentiment (pilot)
7

## Slide 8
Q1–Q2 FY28 · Full Platform
July – December 2027
PHASE 3 — Full Platform · ★ $1.25M ARR milestone (Q1 FY28) · 102 active FI subscriptions
DATA INGESTION
All Data Sources
✓ Fully operational — all rails, core, Banno, lending
Cross-FI Network Intelligence
✓ Benchmarking aggregated across 1,660 FIs
Horizon Data Expansion
Open data — NCUA 5300, external signals (future)
APP DELIVERY
Full App Suite — 5 Core Apps
★ $1.25M ARR Q1 FY28 — 102 subscriptions · 6.1% penetration
FI Decision Studio GA
✓ AutoML at scale — SHAP + rule authoring deployed
Horizon Apps (pilot to GA)
Cross-Sell Propensity, Fraud Ring Detection, Deposit Runoff
Bundle Pricing — Year 2
Intelligence+ bundle conversation with 50+ FI subscriber base
Net-new FI Acquisition
Expansion beyond migrated base — full 1,660 FI penetration
8